## plan-forkommune
Item | Start_date | End_date | Year | Month | Action | RCN_cat | Type | WP | Milestone | Institution | Researcher | Project_costs | Applied_costs
1 |  |  | 2019 | 9 |  | Personal- og indirekte kostnader | Labor | 3 |  | UiB | Professor | 180000 | 0
2 |  |  | 2019 | 9 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 86520 | 86520 | Overføre kr. 53000,-
3 |  |  | 2019 | 9 | Kickoff seminar | Andre driftskostnader | Planning | 1 | 1 | NORCE |  | 120000 | 115000 | kr. 39000, rest 76000 til transkribering?
4 |  |  | 2019 | 9 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 88000 | 0 |  | 76000
5 |  |  | 2019 | 10 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 86520 | 86520 |  | 53000
6 |  |  | 2019 | 10 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 146640 | 146640 |  | 2000
7 |  |  | 2019 | 10 |  | Personal- og indirekte kostnader | Labor | 5 |  | Bergen municipality |  | 88000 | 0
8 |  |  | 2019 | 11 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 146640 | 146640 |  | 15000
9 |  |  | 2019 | 11 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 146640 | 146640 |  | 146000
10 |  |  | 2019 | 11 | Present project experiences and plans Norwegian municipalities | Andre driftskostnader | Dissemination output | 5 |  | NORCE |  | 13000 | 13000 | Overfører kr. 2000
11 |  |  | 2019 | 11 | Survey of citizens of Bergen, part I | Innkjøp av FoU-tjenester | Data collection | 2 | 1 | NORCE |  | 75000 | 75000 | kr 75 000 flyttes til 2020
12 |  |  | 2019 | 12 | Software/hardware/books/subscriptions | Andre driftskostnader | Material | 1 |  | NORCE |  | 0 | 0 | overføres
13 | 2019.09.01 | 2019.12.01 | 2019 | 12 | Questionnaire development | Personal- og indirekte kostnader |  | 2
14 | 2019.12.01 | 2019.12.17 | 2019 | 12 | Survey pilot and testing | Personal- og indirekte kostnader |  | 2
15 |  |  | 2020 | 1 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 76000 | 76000
16 |  |  | 2020 | 1 | Survey of citizens of Bergen, part II | [6 empty] | 75000 | 75000
17 |  |  | 2020 | 1
18 | 2019.12.17 | 2020.01.14 | 2020 | 1 | Field survey and prepare data set | Andre driftskostnader |  | 2
19 |  |  | 2020 | 2 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 90640 | 0
20 |  |  | 2020 | 3 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 151039 | 151039
21 |  |  | 2020 | 3 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 89116 | 89116
22 |  |  | 2020 | 3 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 90640 | 0
23 |  |  | 2020 | 3 | Retrieve population registry data on invited Byborgerpanel participants | Andre driftskostnader | Data collection | 2 | 1 | NORCE |  | 70000 | 70000
24 |  |  | 2020 | 3 | Byborgerpanel, municipal level | Andre driftskostnader | Data collection | 1 |  | NORCE |  | 150000 | 150000
25 |  |  | 2020 | 3 | Byborgerpanel, sub-municipal level | Andre driftskostnader | Data collection | 1 |  | NORCE |  | 150000 | 150000
26 | 2020.01.14 | 2020.03.01 | 2020 | 3 | Analyze data and write report | Personal- og indirekte kostnader |  | 2
27 |  |  | 2020 | 4 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 151039 | 151039
28 |  |  | 2020 | 4 |  | Personal- og indirekte kostnader | Labor | 4 |  | UiB | Professor | 185400 | 0
29 |  |  | 2020 | 4 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 19116 | 19116
30 |  |  | 2020 | 4 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 151039 | 151039
31 |  |  | 2020 | 4 | Deliberative Polling planning and collaboration (at Stanford University) | Andre driftskostnader | Planning | 1 |  | NORCE |  | 250000 | 250000
32 |  |  | 2020 | 4 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 93359 | 0
33 |  |  | 2020 | 5 | Scientific article: Experiences with Byborgerpanel pilot |  | Scientific output | 5 |  | NORCE |  | 0 | 0
34 |  |  | 2020 | 6
35 |  |  | 2020 | 7 |  | Personal- og indirekte kostnader | Labor | 4 |  | NORCE | Researcher II | 151039 | 151039
36 |  |  | 2020 | 8 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 151039 | 151039
37 |  |  | 2020 | 9
38 |  |  | 2020 | 10 | Software/hardware/books/subscriptions | Andre driftskostnader | Material | 1 |  | NORCE |  | 15040 | 15040
39 |  |  | 2020 | 10
40 | 2020.09.01 | 2020.11.01 | 2020 | 11 | Handbook | Personal- og indirekte kostnader |  | 5
41 |  |  | 2020 | 12 | Software/hardware/books/subscriptions | Andre driftskostnader | Material | 1 |  | NORCE |  | 25000 | 25000
42 | 2022.02.01 | 2022.03.01 | 2020 | 12 | Interview local politicians and officials | Personal- og indirekte kostnader |  | 4
43 |  |  | 2021 | 1
44 | 2021.11.01 | 2021.12.01 | 2021 | 1 | Field survey and prepare data set | Andre driftskostnader |  | 2
45 |  |  | 2021 | 2 |  | Personal- og indirekte kostnader | Labor | 4 |  | NORCE | Researcher II | 155570 | 155570
46 |  |  | 2021 | 2 |  | Personal- og indirekte kostnader | Labor | 3 |  | Bergen municipality |  | 93359 | 0
47 | 2021.01.15 | 2021.02.28 | 2021 | 2 | Recruit participants | Personal- og indirekte kostnader |  | 3
48 |  |  | 2021 | 3 |  | Personal- og indirekte kostnader | Labor | 3 |  | NORCE | Research assistant | 91789 | 91789
49 |  |  | 2021 | 3 | Retrieve population registry data on invited participants | Andre driftskostnader | Data collection | 2 | 1 | NORCE |  | 70000 | 70000
50 |  |  | 2021 | 3 |  | Personal- og indirekte kostnader | Labor | 3 |  | Bergen municipality |  | 93359 | 0
51 | 2020.11.01 | 2021.03.01 | 2021 | 3 | Produce information material | Personal- og indirekte kostnader |  | 3
52 | 2020.05.01 | 2021.03.15 | 2021 | 3 | Adapt online platform to Norwegian context | Personal- og indirekte kostnader |  | 3
53 |  |  | 2021 | 4 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 155570 | 155570
54 |  |  | 2021 | 4 |  | Personal- og indirekte kostnader | Labor | 3 |  | UiB | Professor | 190962 | 0
55 |  |  | 2021 | 4 |  | Personal- og indirekte kostnader | Labor | 3 |  | NORCE | Research assistant | 91789 | 91789
56 |  |  | 2021 | 4 | Byborgerpanel: Online Deliberative Polling | Andre driftskostnader | Data collection | 3 | 1 | NORCE |  | 500000 | 500000
57 |  |  | 2021 | 4 |  | Personal- og indirekte kostnader | Labor | 3 |  | Bergen municipality |  | 93359 | 0
58 | 2021.04.01 | 2021.04.30 | 2021 | 4 | Online Deliberative Poll | Andre driftskostnader |  | 3
59 |  |  | 2021 | 5
60 |  |  | 2021 | 6 | Present project experiences and plans Norwegian municipalities | Andre driftskostnader | Dissemination output | 5 |  | NORCE |  | 2000 | 2000
61 |  |  | 2021 | 6 | Present project experiences and plans to Norwegian municipalities | Andre driftskostnader | Dissemination output | 5 | 1 | NORCE |  | 15000 | 15000
62 |  |  | 2021 | 6
63 |  |  | 2021 | 6 | Mid-term seminar | Andre driftskostnader | Planning | 1 | 1 | NORCE |  | 110000 | 104000
64 | 2021.05.01 | 2021.06.10 | 2021 | 6 | Prepare mid-term seminar | Personal- og indirekte kostnader |  | 1
65 |  |  | 2021 | 7
66 | 2021.05.01 | 2021.07.01 | 2021 | 7 | Handbook | Personal- og indirekte kostnader |  | 5
67 | 2021.06.01 | 2021.07.01 | 2021 | 7 | Present experiences to municipalities | Personal- og indirekte kostnader |  | 5
68 |  |  | 2021 | 8 | Conference presentation: Experiments on recruitment strategies, participation, and legitimacy of democratic innovations | Andre driftskostnader | Scientific output | 2 | 1 | NORCE |  | 100000 | 100000
69 |  |  | 2021 | 8 |  | Personal- og indirekte kostnader | Labor | 5 |  | Bergen municipality |  | 93359 | 0
70 |  |  | 2021 | 9 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 155570 | 155570
71 |  |  | 2021 | 10 |  | Personal- og indirekte kostnader | Labor | 2 |  | NORCE | P.I. | 155570 | 155570
72 |  |  | 2021 | 10 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Research assistant | 91789 | 91789
73 |  |  | 2021 | 10 | Scientific research publication: Experiments on recruitment strategies, participation, and legitimacy of democratic innovations |  | Scientific output | 2 | 1 | NORCE
74 |  |  | 2021 | 11 | Present project experiences and plans Norwegian municipalities | Andre driftskostnader | Dissemination output | 5 | 1 | NORCE |  | 15000 | 15000
75 |  |  | 2021 | 11 | Survey of citizens of Bergen/Norway | Innkjøp av FoU-tjenester | Data collection | 2 | 1 | NORCE |  | 130000 | 130000
76 |  |  | 2021 | 12 | Software/hardware/books/subscriptions | Andre driftskostnader | Material | 1 |  | NORCE |  | 25000 | 25000
77 | 2021.08.01 | 2021.10.01 | 2021 | 12 | Questionnaire development | Personal- og indirekte kostnader |  | 2
78 | 2021.10.01 | 2021.11.01 | 2021 | 12 | Survey pilot and testing | Personal- og indirekte kostnader |  | 2
79 |  |  | 2022 | 1 | Conference participation | Andre driftskostnader | Scientific output | 1 |  | NORCE |  | 50000 | 50000
80 |  |  | 2022 | 2 |  | Personal- og indirekte kostnader | Labor | 4 |  | NORCE | Researcher II | 160237 | 160237
81 |  |  | 2022 | 2 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 96159 | 0
82 |  |  | 2022 | 3 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | Research assistant | 94543 | 94543
83 |  |  | 2022 | 3 |  | Personal- og indirekte kostnader | Labor | 1 |  | Bergen municipality |  | 96159 | 0
84 |  |  | 2022 | 3 | Survey of local politicians and officials on the impact of Byborgerpanel | Andre driftskostnader | Data collection | 4 | 1 | NORCE |  | 20000 | 20000
85 | 2022.01.01 | 2022.03.01 | 2022 | 3 | Handbook | Personal- og indirekte kostnader |  | 5
86 |  |  | 2022 | 4 |  | Personal- og indirekte kostnader | Labor | 1 |  | NORCE | P.I. | 160237 | 160237
87 |  |  | 2022 | 4 |  | Personal- og indirekte kostnader | Labor | 4 |  | UiB | Professor | 196691 | 0
88 |  |  | 2022 | 4 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Research assistant | 94543 | 94543
89 |  |  | 2022 | 4 |  | Personal- og indirekte kostnader | Labor | 5 |  | Bergen municipality |  | 96159 | 0
90 |  |  | 2022 | 5 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 160237 | 160237
91 |  |  | 2022 | 6
92 |  |  | 2022 | 7 |  | Personal- og indirekte kostnader | Labor | 5 |  | NORCE | Researcher II | 160237 | 160237
93 |  |  | 2022 | 8 |  | Personal- og indirekte kostnader | Labor | 5 |  | Bergen municipality |  | 96159 | 0
94 |  |  | 2022 | 9 |  | Personal- og indirekte kostnader | Labor | 4 |  | NORCE | Researcher II | 160237 | 160237
95 |  |  | 2022 | 10 | Scientific research publication: Tracing the influecne of the Byborgerpanel in the local decision-making process |  | Scientific output | 4 |  | NORCE
96 |  |  | 2022 | 10 | Scientific research publication: Deliberative Polling in Norway |  | Scientific output | 3 |  | NORCE
97 |  |  | 2022 | 11 | Publish handbook | Andre driftskostnader | Dissemination output | 5 | 1 | NORCE |  | 50000 | 50000
98 |  |  | 2022 | 11 | End conference | Andre driftskostnader | Dissemination output | 5 | 1 | NORCE |  | 120000 | 115000