## plan-forkommune
Item | Start_date | End_date | Year | Month | Action | Type | WP | Milestone | NORCE | Bergen | UofB | Project_costs | Applied_costs
1 | 2019.10.01 | 2020.10.17 | 2019 | 9 | Kickoff seminar | Planning | 1 | 1 |  |  |  | 100000 | 100000
2 |  |  | 2019 | 9 |  | Labor | 1 |  | 1 |  |  | 140542 | 140542
3 |  |  | 2019 | 9 |  | Labor | 1 |  | 1 |  |  | 140542 | 140542
4 |  |  | 2019 | 9 |  | Labor | 1 |  |  | 1 |  | 88000 | 0
5 |  |  | 2019 | 9 |  | Labor | 1 |  |  |  | 1 | 180000 | 0
6 |  |  | 2019 | 10 |  | Labor | 2 |  | 1 |  |  | 140542 | 140542
7 |  |  | 2019 | 10 |  | Labor | 2 |  | 1 |  |  | 140542 | 140542
8 | 2019.09.01 | 2019.12.01 | 2019 | 12 | Questionnaire development |  | 2
9 | 2019.12.01 | 2019.12.17 | 2019 | 12 | Survey pilot and testing |  | 2
10 | 2019.12.17 | 2020.01.14 | 2020 | 1 | Field survey and prepare data set |  | 2
11 | 2020.01.14 | 2020.03.01 | 2020 | 3 | Analyze data and write report |  | 2
12 | 2020.09.01 | 2020.11.01 | 2020 | 11 | Handbook |  | 5
13 | 2020.09.01 | 2020.12.15 | 2020 | 12 | Interview local politicians and officials |  | 4
14 | 2021.11.01 | 2021.12.01 | 2021 | 1 | Field survey and prepare data set |  | 2
15 | 2021.01.15 | 2021.02.28 | 2021 | 2 | Recruit participants |  | 3
16 | 2020.11.01 | 2021.03.01 | 2021 | 3 | Produce information material |  | 3
17 | 2020.05.01 | 2021.03.15 | 2021 | 3 | Learn and adapt online platform to Norwegian context |  | 3
18 | 2021.04.01 | 2020.04.30 | 2021 | 4 | Online Deliberative Poll |  | 3
19 | 2021.05.01 | 2021.06.10 | 2021 | 6 | Prepare mid-term seminar |  | 1
20 | 2021.05.01 | 2020.07.01 | 2021 | 7 | Handbook |  | 3
21 | 2021.06.01 | 2022.07.01 | 2021 | 7 | Present experiences to municipalities
22 | 2021.08.01 | 2021.10.01 | 2021 | 12 | Questionnaire development |  | 2
23 | 2021.10.01 | 2021.11.01 | 2021 | 12 | Survey pilot and testing |  | 2
24 | 2022.01.01 | 2022.03.01 | 2022 | 3 | Handbook |  | 2
25
26
27
28
29 | 2019 |  | 2019 | 10 | Survey of local politicians and officials on the expected impact of Byborgerpanel
30 |  |  | 2019 | 10 |  | Labor | 5 |  |  | 1 |  | 88000 | 0
31 |  |  | 2019 | 11 |  | Labor | 2 |  | 1 |  |  | 140542 | 140542
32 |  |  | 2019 | 11 |  | Labor | 2 |  | 1 |  |  | 140542 | 140542
33 |  |  | 2019 | 11 | Present project experiences and plans Norwegian municipalities | Dissemination output | 5 | 1 |  |  |  | 15000 | 15000
34 |  |  | 2019 | 11 | Survey of citizens of Bergen | Data collection | 2 | 1 |  |  |  | 200000 | 200000
35 |  |  | 2019 | 12 | Software/hardware/books/subscriptions | Material | 1 |  |  |  |  | 25000 | 25000
36 |  |  | 2020 | 1 | Research exchange Stanford University | Planning | 1 |  |  |  |  | 270000 | 270000
37 |  |  | 2020 | 2 |  | Labor | 1 |  |  | 1 |  | 90640 | 0
38 |  |  | 2020 | 3 |  | Labor | 1 |  | 2 |  |  | 89116 | 89116
39 |  |  | 2020 | 3 |  | Labor | 1 |  |  | 1 |  | 90640 | 0
40 |  |  | 2020 | 3 |  | Labor | 1 |  | 1 |  |  | 144758 | 144758
41 |  |  | 2020 | 3 | Retrieve population registry data on invited Byborgerpanel participants | Data collection | 2 | 1 |  |  |  | 70000 | 70000
42 |  |  | 2020 | 3 | Byborgerpanel, municipal level | Data collection | 1 | 1 |  |  |  | 150000 | 150000
43 |  |  | 2020 | 3 | Byborgerpanel, bydel level | Data collection | 1 | 1 |  |  |  | 150000 | 150000
44 |  |  | 2020 | 3 | Byborgerpanel, valgkrets level | Data collection | 1 | 1 |  |  |  | 150000 | 150000
45 |  |  | 2020 | 4 |  | Labor | 1 |  |  |  | 1 | 185400 | 0
46 |  |  | 2020 | 4 |  | Labor | 2 |  | 1 |  |  | 144758 | 144758
47 |  |  | 2020 | 4 |  | Labor | 1 |  | 2 |  |  | 19116 | 19116
48 |  |  | 2020 | 4 |  | Labor | 1 |  |  | 1 |  | 93359 | 0
49 |  |  | 2020 | 5
50 |  |  | 2020 | 6
51 |  |  | 2020 | 7
52 |  |  | 2020 | 8 | Conference presentation: Experiments on recruitment strategies, participation, and legitimacy of democratic innovations | Scientific output | 2 | 1 |  |  |  | 100000 | 100000
53 |  |  | 2020 | 8 |  | Labor | 4 |  | 1 |  |  | 144758 | 144758
54 |  |  | 2020 | 9
55 |  |  | 2020 | 11 | Present project experiences and plans to Norwegian municipalities | Dissemination output | 5 | 1 |  |  |  | 15000 | 15000
56 |  |  | 2020 | 12 | Software/hardware/books/subscriptions | Material | 1 |  |  |  |  | 25000 | 25000
57 |  |  | 2021 | 1
58 |  |  | 2021 | 2 |  | Labor | 4 |  | 1 |  |  | 149101 | 149101
59 |  |  | 2021 | 2 |  | Labor | 3 |  |  | 1 |  | 93359 | 0
60 |  |  | 2021 | 3 | Retrieve population registry data on invited participants | Data collection | 2 | 1 |  |  |  | 70000 | 70000
61 |  |  | 2021 | 3 |  | Labor | 3 |  | 2
62 |  |  | 2021 | 3 |  | Labor | 3 |  |  | 1 |  | 93359 | 0
63 |  |  | 2021 | 4 | Byborgerpanel: Deliberative Polling | Data collection | 3 | 1 |  |  |  | 500000 | 500000
64 |  |  | 2021 | 4 |  | Labor | 3 |  | 1 |  |  | 149101 | 149101
65 |  |  | 2021 | 4 |  | Labor | 3 |  | 2 |  |  | 91789 | 91789
66 |  |  | 2021 | 4 |  | Labor | 3 |  |  | 1 |  | 93359 | 0
67 |  |  | 2021 | 4 |  | Labor | 3 |  |  |  | 1 | 190962 | 0
68 |  |  | 2021 | 5
69 |  |  | 2021 | 6
70 |  |  | 2021 | 7
71 |  |  | 2021 | 8 |  | Labor | 5 |  |  | 1 |  | 93359 | 0
72 |  |  | 2021 | 8 |  | Labor | 4 |  | 1 |  |  | 149101 | 149101
73 |  |  | 2021 | 6 | Mid-term seminar | Planning | 1 | 1 |  |  |  | 50000 | 50000
74 |  |  | 2021 | 9 |  | Labor | 1 |  | 1 |  |  | 149101 | 149101
75 |  |  | 2021 | 10 | International peer reviewed article: Experiments on recruitment strategies, participation, and legitimacy of democratic innovations | Scientific output | 2 | 1
76 |  |  | 2021 | 10 |  | Labor | 5 |  | 1 |  |  | 149101 | 149101
77 |  |  | 2021 | 11 | Present project experiences and plans Norwegian municipalities | Dissemination output | 5 | 1 |  |  |  | 15000 | 15000
78 |  |  | 2021 | 11 | Survey of citizens of Bergen | Data collection | 2 | 1 |  |  |  | 200000 | 200000
79 |  |  | 2021 | 12 | Software/hardware/books/subscriptions | Material | 1 |  |  |  |  | 25000 | 25000
80 |  |  | 2022 | 1 | Conference participation | Scientific output | 1 |  |  |  |  | 50000 | 50000
81 |  |  | 2022 | 2 |  | Labor | 4 |  | 1 |  |  | 153574 | 153574
82 |  |  | 2022 | 2 |  | Labor | 1 |  |  | 1 |  | 96159 | 0
83 |  |  | 2022 | 3 |  | Labor | 1 |  | 2 |  |  | 94543 | 94543
84 |  |  | 2022 | 3 |  | Labor | 1 |  |  | 1 |  | 96159 | 0
85 |  |  | 2022 | 3 | Survey of local politicians and officials on the impact of Byborgerpanel | Data collection | 4 | 1
86 |  |  | 2022 | 4 |  | Labor | 1 |  | 1 |  |  | 153574 | 153574
87 |  |  | 2022 | 4 |  | Labor | 5 |  | 2 |  |  | 94543 | 94543
88 |  |  | 2022 | 4 |  | Labor | 3 |  |  |  | 1 | 196691 | 0
89 |  |  | 2022 | 4 |  | Labor | 5 |  |  | 1 |  | 96159 | 0
90 |  |  | 2022 | 5 |  | Labor | 5 |  | 1 |  |  | 153574 | 153574
91 |  |  | 2022 | 6
92 |  |  | 2022 | 7 |  | Labor | 2 |  | 1 |  |  | 153574 | 153574
93 |  |  | 2022 | 8 |  | Labor | 5 |  |  | 1 |  | 96159 | 0
94 |  |  | 2022 | 9 |  | Labor | 4 |  | 1 |  |  | 153574 | 153574
95 |  |  | 2022 | 11 | Publish handbook | Dissemination output | 5 | 1 |  |  |  | 50000 | 50000
96 |  |  | 2022 | 11 | End conference | Dissemination output | 5 | 1 |  |  |  | 100000 | 100000